## Table of Contents
TI Information - Selective Disclosure
Copyright (C) 2023 Texas Instruments Incorporated
Sheet No. | Title | Purpose
1 | Table of Contents | Provides an overview of the contents of the complete report.
2 | Script Input Parameters | Displays the input parameters provided to generate this report.
3 | Coverage Summary | Provides a summary report of Coverage for both Forward and Backward Traceability.
4 | Forward Traceability | Provides the detailed Forward Traceability Report from Marketing Requirements(MRD) to Software Product Specifications(SPS) & from Software Product Specifications(SPS) to Test Cases.
5 | Backward Traceability | Provides the detailed Backward Traceability Report from Software Product Specifications(SPS) to Marketing Requirements(MRD) & from Test Cases to Software Product Specifications(SPS).
6 | Traceability Deviations | Provides the details of all the Traceability Deviations.
7 | Revision History | Provides Template Revision History.

## Script Input Parameters
CM Record Key | Baseline Project Key | Report generated on
ETHFW-2377 | ETHFW | 2023-07-26 08:04:40.714625-05:00 CDT

## Coverage Summary
Forward Coverage Type | Forward Percentage Covered | Backward Coverage Type | Backward Percentage Covered
Marketing Requirement (MRD) -> Software Product Specification (SPS) | 100.0% | Software Product Specification (SPS) -> Marketing Requirement (MRD) | 100.0%
Software Product Specification (SPS) -> Test Case | 91.67% | Test Case -> Software Product Specification (SPS) | 100.0%

## Forward Traceability
MRD ID | SPS ID(s) | SPS ID | Test Case ID(s) | Test Case Scope
JACINTOREQ-661 | ETHFW-1920 | ETHFW-1920 | ETHFW-1663 | Unit
JACINTOREQ-1166 | ETHFW-1716,ETHFW-1721 | ETHFW-1716 | ETHFW-1823 | Unit
JACINTOREQ-4611 | ETHFW-1716,ETHFW-903,ETHFW-1742,ETHFW-1253,ETHFW-1196,ETHFW-1711,ETHFW-1143,ETHFW-955,ETHFW-1721,ETHFW-1302,ETHFW-1203,ETHFW-843,ETHFW-937,ETHFW-1110,ETHFW-1713,ETHFW-1170,ETHFW-1237,ETHFW-1168,ETHFW-1290,ETHFW-1154,ETHFW-1255,ETHFW-1856,ETHFW-1245,ETHFW-1184,ETHFW-1947,ETHFW-1232,ETHFW-1288,ETHFW-1287,ETHFW-1718,ETHFW-1277,ETHFW-1280,ETHFW-1179,ETHFW-1119,ETHFW-899 | ETHFW-903 | ETHFW-1415,ETHFW-1927,ETHFW-1928,ETHFW-1930,ETHFW-1931,ETHFW-1932 | Unit,Integration,Integration,Integration,Integration,Integration
JACINTOREQ-380 | ETHFW-903,ETHFW-941,ETHFW-955,ETHFW-843,ETHFW-937,ETHFW-899 | ETHFW-941 | ETHFW-1424 | Unit
JACINTOREQ-1168 | ETHFW-1742 | ETHFW-1742 | ETHFW-1823,ETHFW-1701 | Unit,Unit
JACINTOREQ-547 | ETHFW-1253,ETHFW-1229,ETHFW-1203,ETHFW-1119 | ETHFW-1253 | ETHFW-1545 | Unit
JACINTOREQ-240 | ETHFW-1196,ETHFW-1302,ETHFW-1110,ETHFW-1154,ETHFW-1255,ETHFW-1232,ETHFW-1277 | ETHFW-1196 | ETHFW-1399 | Unit
JACINTOREQ-1102 | ETHFW-1711,ETHFW-1712 | ETHFW-1711 | ETHFW-1900,ETHFW-1899 | Unit,Unit
JACINTOREQ-3547 | ETHFW-1193,ETHFW-1740 | ETHFW-1193 | ETHFW-1887,ETHFW-1886 | Unit,Unit
JACINTOREQ-494 | ETHFW-1193,ETHFW-1740 | ETHFW-1143 | ETHFW-1025 | Unit
JACINTOREQ-378 | ETHFW-1143,ETHFW-955,ETHFW-1170,ETHFW-1237,ETHFW-1148,ETHFW-1168,ETHFW-1290,ETHFW-1245,ETHFW-1184,ETHFW-1288,ETHFW-1280 | ETHFW-1229 | ETHFW-1552 | Unit
JACINTOREQ-3525 | ETHFW-1229 | ETHFW-1211 | ETHFW-1887,ETHFW-1886 | Unit,Unit
JACINTOREQ-3549 | ETHFW-1211,ETHFW-1726,ETHFW-1739 | ETHFW-955 | ETHFW-1405 | Unit
JACINTOREQ-493 | ETHFW-1211,ETHFW-1739 | ETHFW-1721
JACINTOREQ-1356 | ETHFW-1726 | ETHFW-1302 | ETHFW-1323 | Unit
JACINTOREQ-3524 | ETHFW-1712 | ETHFW-1726 | ETHFW-1895 | Unit
JACINTOREQ-550 | ETHFW-607 | ETHFW-1203 | ETHFW-1331 | Unit
JACINTOREQ-903 | ETHFW-607 | ETHFW-1712 | ETHFW-1900,ETHFW-1899 | Unit,Unit
JACINTOREQ-906 | ETHFW-607 | ETHFW-843 | ETHFW-1427 | Unit
JACINTOREQ-551 | ETHFW-1273 | ETHFW-607 | ETHFW-1663 | Unit
JACINTOREQ-818 | ETHFW-1713 | ETHFW-937 | ETHFW-1344 | Unit
JACINTOREQ-1528 | ETHFW-1856 | ETHFW-1273 | ETHFW-1834 | Unit
JACINTOREQ-549 | ETHFW-1287,ETHFW-1293 | ETHFW-1110 | ETHFW-1326 | Unit
JACINTOREQ-1212 | ETHFW-1718 | ETHFW-1713
JACINTOREQ-546 | ETHFW-1179 | ETHFW-1739 | ETHFW-1887,ETHFW-1886 | Unit,Unit
JACINTOREQ-678 | ETHFW-1119 | ETHFW-1170 | ETHFW-1330 | Unit
JACINTOREQ-1378 | ETHFW-1878 | ETHFW-1740 | ETHFW-1886,ETHFW-1887 | Unit,Unit
JACINTOREQ-2619 | ETHFW-1878 | ETHFW-1237 | ETHFW-2367 | Unit
JACINTOREQ-3522 | ETHFW-1293 | ETHFW-1148 | ETHFW-987 | Unit
|  | ETHFW-1168 | ETHFW-1058 | Unit
|  | ETHFW-1290 | ETHFW-1355 | Unit
|  | ETHFW-1154 | ETHFW-1362 | Unit
|  | ETHFW-1255 | ETHFW-1419 | Unit
ETHFW-1856
|  | ETHFW-1245 | ETHFW-1030 | Unit
|  | ETHFW-1184 | ETHFW-1097 | Unit
|  | ETHFW-1947 | ETHFW-2009,ETHFW-2010 | Unit,Unit
|  | ETHFW-1232 | ETHFW-1401 | Unit
|  | ETHFW-1288 | ETHFW-1010 | Unit
|  | ETHFW-1287 | ETHFW-1542 | Unit
|  | ETHFW-1718 | ETHFW-1823 | Unit
|  | ETHFW-1277 | ETHFW-1342 | Unit
|  | ETHFW-1280 | ETHFW-1094 | Unit
|  | ETHFW-1179 | ETHFW-1664 | Unit
|  | ETHFW-1119 | ETHFW-1547 | Unit
ETHFW-1878
|  | ETHFW-899 | ETHFW-1325 | Unit
|  | ETHFW-1293 | ETHFW-1551 | Unit

## Backward Traceability
SPS ID | MRD ID(s) | Test Case ID | Test Case Scope | SPS ID(s)
ETHFW-1920 | JACINTOREQ-661 | ETHFW-1932 | Integration | ETHFW-903
ETHFW-1716 | JACINTOREQ-1166,JACINTOREQ-4611 | ETHFW-1058 | Unit | ETHFW-1168
ETHFW-903 | JACINTOREQ-380,JACINTOREQ-4611 | ETHFW-1424 | Unit | ETHFW-941
ETHFW-941 | JACINTOREQ-380 | ETHFW-1834 | Unit | ETHFW-1948
ETHFW-1742 | JACINTOREQ-1168,JACINTOREQ-4611 | ETHFW-1415 | Unit | ETHFW-903
ETHFW-1253 | JACINTOREQ-4611,JACINTOREQ-547 | ETHFW-1010 | Unit | ETHFW-1288
ETHFW-1196 | JACINTOREQ-240,JACINTOREQ-4611 | ETHFW-1030 | Unit | ETHFW-1245
ETHFW-1711 | JACINTOREQ-1102,JACINTOREQ-4611 | ETHFW-1405 | Unit | ETHFW-955
ETHFW-1193 | JACINTOREQ-3547,JACINTOREQ-494 | ETHFW-1025 | Unit | ETHFW-1143
ETHFW-1143 | JACINTOREQ-378,JACINTOREQ-4611 | ETHFW-1427 | Unit | ETHFW-843
ETHFW-1229 | JACINTOREQ-3525,JACINTOREQ-547 | ETHFW-1344 | Unit | ETHFW-937
ETHFW-1211 | JACINTOREQ-3549,JACINTOREQ-493 | ETHFW-987 | Unit | ETHFW-1148
ETHFW-955 | JACINTOREQ-378,JACINTOREQ-380,JACINTOREQ-4611 | ETHFW-1326 | Unit | ETHFW-1110
ETHFW-1721 | JACINTOREQ-1166,JACINTOREQ-4611 | ETHFW-1362 | Unit | ETHFW-1154
ETHFW-1302 | JACINTOREQ-240,JACINTOREQ-4611 | ETHFW-1419 | Unit | ETHFW-1255
ETHFW-1726 | JACINTOREQ-1356,JACINTOREQ-3549 | ETHFW-1399 | Unit | ETHFW-1196
ETHFW-1203 | JACINTOREQ-4611,JACINTOREQ-547 | ETHFW-1097 | Unit | ETHFW-1184
ETHFW-1712 | JACINTOREQ-1102,JACINTOREQ-3524 | ETHFW-1323 | Unit | ETHFW-1302
ETHFW-843 | JACINTOREQ-380,JACINTOREQ-4611 | ETHFW-1330 | Unit | ETHFW-1170
ETHFW-607 | JACINTOREQ-550,JACINTOREQ-903,JACINTOREQ-906 | ETHFW-1401 | Unit | ETHFW-1232
ETHFW-937 | JACINTOREQ-380,JACINTOREQ-4611 | ETHFW-1342 | Unit | ETHFW-1277
ETHFW-1273 | JACINTOREQ-551 | ETHFW-1355 | Unit | ETHFW-1290
ETHFW-1110 | JACINTOREQ-240,JACINTOREQ-4611 | ETHFW-1886 | Unit | ETHFW-1112,ETHFW-1739,ETHFW-1211,ETHFW-1193
ETHFW-1713 | JACINTOREQ-4611,JACINTOREQ-818 | ETHFW-1887 | Unit | ETHFW-1112,ETHFW-1211,ETHFW-1739,ETHFW-1193
ETHFW-1739 | JACINTOREQ-3549,JACINTOREQ-493 | ETHFW-2367 | Unit | ETHFW-1237
ETHFW-1170 | JACINTOREQ-378,JACINTOREQ-4611 | ETHFW-1542 | Unit | ETHFW-1287
ETHFW-1740 | JACINTOREQ-3547,JACINTOREQ-494 | ETHFW-1663 | Unit | ETHFW-607,ETHFW-1920
ETHFW-1237 | JACINTOREQ-378,JACINTOREQ-4611 | ETHFW-1664 | Unit | ETHFW-1179
ETHFW-1148 | JACINTOREQ-378 | ETHFW-1895 | Unit | ETHFW-1726
ETHFW-1168 | JACINTOREQ-378,JACINTOREQ-4611 | ETHFW-1899 | Unit | ETHFW-1958,ETHFW-1711
ETHFW-1290 | JACINTOREQ-378,JACINTOREQ-4611 | ETHFW-1900 | Unit | ETHFW-1711,ETHFW-1712
ETHFW-1154 | JACINTOREQ-240,JACINTOREQ-4611 | ETHFW-2009 | Unit | ETHFW-1952
ETHFW-1255 | JACINTOREQ-240,JACINTOREQ-4611 | ETHFW-2010 | Unit | ETHFW-1947
ETHFW-1856 | JACINTOREQ-1528,JACINTOREQ-4611 | ETHFW-1927 | Integration | ETHFW-903
ETHFW-1245 | JACINTOREQ-378,JACINTOREQ-4611 | ETHFW-1094 | Unit | ETHFW-1280
ETHFW-1184 | JACINTOREQ-378,JACINTOREQ-4611 | ETHFW-1930 | Integration | ETHFW-903
ETHFW-1947 | JACINTOREQ-4611 | ETHFW-1931 | Integration | ETHFW-903
ETHFW-1232 | JACINTOREQ-240,JACINTOREQ-4611 | ETHFW-1928 | Integration | ETHFW-903
ETHFW-1288 | JACINTOREQ-378,JACINTOREQ-4611 | ETHFW-1701 | Unit | ETHFW-1686
ETHFW-1287 | JACINTOREQ-4611,JACINTOREQ-549 | ETHFW-1545 | Unit | ETHFW-1253
ETHFW-1718 | JACINTOREQ-1212,JACINTOREQ-4611 | ETHFW-1547 | Unit | ETHFW-1119
ETHFW-1277 | JACINTOREQ-240,JACINTOREQ-4611 | ETHFW-1551 | Unit | ETHFW-1293
ETHFW-1280 | JACINTOREQ-378,JACINTOREQ-4611 | ETHFW-1552 | Unit | ETHFW-1229
ETHFW-1179 | JACINTOREQ-4611,JACINTOREQ-546 | ETHFW-1325 | Unit | ETHFW-899
ETHFW-1119 | JACINTOREQ-4611,JACINTOREQ-547,JACINTOREQ-678 | ETHFW-1331 | Unit | ETHFW-1203
ETHFW-1878 | JACINTOREQ-1378,JACINTOREQ-2619 | ETHFW-1823 | Unit | ETHFW-1966,ETHFW-1716,ETHFW-1742
ETHFW-899 | JACINTOREQ-380,JACINTOREQ-4611
ETHFW-1293 | JACINTOREQ-3522,JACINTOREQ-549

## Traceability Deviations
Coverage Type | Parameter ID(s) | Justification for Traceability Deviation
Software Product Specification (SPS) -> Test Case | ETHFW-1721 | Not a testable case, ETHFW makes all OS calls via OSAL layer, verified by code inspection
Software Product Specification (SPS) -> Test Case | ETHFW-1713 | This feature is not testable on TI EVMs, only docs update are done.
Software Product Specification (SPS) -> Test Case | ETHFW-1856 | This is just a documentation update, cannot be tested.
Software Product Specification (SPS) -> Test Case | ETHFW-1878 | This is just a documentation update, cannot be tested.

## Template Revision History
Author | Version | Date | Description
Krishna/ Dhruv | A | 20/1/2023 | Initial version